## Bid Form
BID FORM CONTRACT NO. 43-22-06
Ref. | Item |  | Approx. |  | Unit | Extended
No. | No. | Item Description | Quantity | Unit | Cost | Bid Amount
GENERAL (Ref. Nos. 1 - 6)
1 | IB.ART.6 | PREMIUM FOR CONTRACT PERFORMANCE BOND AND PAYMENT BOND | 1 | LUMP
2 | SP 614 | MAINTAINING TRAFFIC | 1 | LUMP
3 | SP 614 | WORK ZONE IMPACT ATTENUATOR FOR 24" WIDE HAZARDS (UNIDIRECTIONAL OR BIDIRECTIONAL) | 4 | EACH
4 | SP 619 | FIELD OFFICE | 1 | LUMP
5 | SP 623 | CONSTRUCTION LAYOUT SURVEY | 1 | LUMP
6 | 624 | MOBILIZATION | 1 | LUMP
TOTAL - GENERAL
ROADWAY (Ref. Nos. 7 - 18)
7 | 202 | CURB REMOVED | 50 | FT
8 | 609 | ASPHALT CONCRETE CURB, TYPE 1 | 50 | FT
9 | 614 | REPLACEMENT SIGNS | 2 | EACH
10 | SP 614ZP | ZONE PERSON WITH ZONE VEHICLE | 3600 | HOURS
11 | SP 614C | REMOVAL OF PAVEMENT MARKINGS | 10.4 | MILES
12 | 630 | SIGNING, MISC.: ADDITIONAL SIGNS WITH SUPPORTS, AS DIRECTED BY THE CHIEF ENGINEER | 500 | SF
13 | 642 | PAVEMENT MARKING MISC.: FINAL PAVEMENT MARKING PREPARATION | 10.4 | MILES
14 | 642 | EDGE LINE, 6", TYPE 1 | 5.2 | MILES
15 | 642 | LANE LINE, 6", TYPE 1 | 5.2 | MILES
16 | SPECIAL | EXISTING CROSSOVER TO BE CLOSED/RE-OPENED | 1 | LUMP
17 | SPECIAL | "SNAP" MILL AND FILL | 10050 | FT
18 | SPECIAL | SONIC NAP ALERT PATTERN (SNAP) | 1.9 | MILES
TOTAL - ROADWAY
STRUCTURES (Ref. Nos. 19 - 34)
19 | SP 202 | PORTIONS OF STRUCTURE REMOVED | 1 | LUMP
20 | SP 509 | EPOXY COATED REINFORCING STEEL, GRADE 60 | 447 | POUND
21 | SP 511B | CLASS S CONCRETE, BARRIERS AND PARAPETS, USING TYPE I CEMENT | 4 | CY
22 | 512 | TREATING CONCRETE BRIDGE DECKS WITH GRAVITY FED RESIN | 36286 | SY
23 | SP 516A | CRACK REPAIR USING EPOXY INJECTION | 1000 | FT
24 | SP 516G | REPLACE EXPANSION BEARING DEVICE | 89 | EACH
25 | SP 516J | REPLACE FIXED BEARING DEVICE | 1 | EACH
26 | 516 | JACKING AND TEMPORARY SUPPORT OF SUPERSTRUCTURE, AS PER PLAN | 1 | LUMP
27 | SP 519 | PATCHING CONCRETE STRUCTURES | 2550 | SF
28 | SP 519C | PATCHING CONCRETE STRUCTURES WITH TROWELABLE MORTAR | 5080 | SF
29 | SP 536 | CONCRETE WEATHERPROOFING, BARRIERS AND PARAPETS, AS PER PLAN | 9990 | SY
30 | SP 536 | CONCRETE WEATHERPROOFING, SUBSTRUCTURE | 345 | SY
31 | 601 | DUMPED ROCK FILL, TYPE D, AS PER PLAN | 500 | CY
32 | 844 | CONCRETE PATCHING WITH GALVANIC ANODE PROTECTION | 68 | SF
33 | SPECIAL | CONTINUOUS STRIP SEAL | 1264 | FT
34 | SPECIAL | MODULAR EXPANSION JOINT | 8 | FT
TOTAL - STRUCTURES
BID SUMMARY
The total amount of the preceding Bid, based upon the approximate quantities given above, and the Unit Prices and Lump Sum specified by the undersigned, amounts to the sum of:
TOTAL BASE BID (INCLUDES REF. NO. 1 THRU REF. NO. 34) ----------------------------------------------->
THE BID, FOR CONTRACT No. 43-22-06, OF UNIT PRICE EXTENSIONS IS ALL LABOR, EQUIPMENT AND MATERIALS, FOR THE SUM OF:
(Sum in words)_____________________________________________________________________________________________DOLLARS
Item No.'s that do not have an IB or SP designation are items drawn from the 2019 ODOT CMS. Bidders should refer to the 2019 ODOT CMS for information and guidance concerning these items.